## Sheet1
|  |  | Duration | % Complete | Start | Finish | Rebaseline
MM Trigger processor Emulation |  |  | 420 |  | 2013-10-01 | 2015-04-20
1.02.04.01 | TRG1010 | Design and simulate single region | 60 | 100% | 2013-10-01 | 2013-12-24
1.02.04.01 | TRG1015 | Design and Simulatoin Validation | 37 | 100% | 2013-12-26 | 2014-02-17
1.02.04.01 | TRG1020 | Implement in FPGA eval board - single region | 30 | 100% | 2014-04-01 | 2014-05-12
1.02.04.01 | TRG1030 | Design and simulate multiple regions | 30 | 100% | 2014-05-13 | 2014-06-24
1.02.04.01 | TRG1040 | Implement in FPGA eval board - multiple regions | 30 | 100% | 2014-06-25 | 2014-08-06
1.02.04.01 | TRG1040M | Material cost for Implement in FPGA eval board | 30 | 100% | 2014-06-25 | 2014-08-06
1.02.04.01 | TRG1049 | Waiting for Funding | 60 | 100% | 2014-04-01 | 2014-06-24
1.02.04.01 | TRG1050 | Plan GBT implementation with BNL engineers | 3 | 100% | 2014-10-01 | 2014-10-03
1.02.04.01 | TRG1060 | Procure optical fiber & transceivers | 10 | 100% | 2014-10-02 | 2014-10-15
1.02.04.01 | TRG1070 | Implement and test on TP emulation board | 30 | 100% | 2014-10-02 | 2014-11-12
1.02.04.01 | TRG1080 | Consult with UA and BNL on ART data format | 10 | 100% | 2014-04-01 | 2014-04-14
1.02.04.01 | TRG1080T | Travel cost for Consult with UA and BNL on ART data format | 10 | 100% | 2014-08-01 | 2014-08-14
1.02.04.01 | TRG1090 | Mini-SAS/FMC mezzanine card | 48 | 100% | 2014-05-01 | 2014-07-09
1.02.04.01 | TRG1100 | Firmware design/test | 21 | 100% | 2014-10-01 | 2014-10-29
1.02.04.01 | TRG1110 | Integrate ART-PG/ADDCE | 60 | 100% | 2014-10-30 | 2015-01-26 | 2015-05-15 | Nathan to confer with Lin to pick a realistic milestone
1.02.04.01 | TRG1110M | Material cost for Integrate ART-PG/ADDCE | 60 | 100% | 2014-10-30 | 2015-01-26
1.02.04.01 | TRG1120 | Integrate real ADDC with 32 GBT links | 60 | 70% | 2015-01-27 | 2015-04-20 | 2016-09-01 | Availability of ADDC?????
1.02.04.01 | TRG1120M | Material cost for Integrate real ADDC with 32 GBT links | 60 | 100% | 2015-01-27 | 2015-04-20
1.02.04.01 | TRG1120T | Travel cost for Integrate real ADDC with 32 GBT links | 60 | 50% | 2015-01-27 | 2015-04-20
1.02.04.01 | TRG1130 | ART Pattern generator complete | 0 | 90% |  | 2015-04-20
1.02.04.01 | TRG2010 | Test beam I | 60 | 0% | 2014-10-01 | 2014-12-24 | ???? | When is next test beam? Will we go there?
1.02.04.01 | TRG2010T | Travel cost for Test beam I | 60 | 0% | 2014-10-01 | 2014-12-24
MM TP ATCA Hardware |  |  | 409 |  | 2015-01-02 | 2016-06-01
1.02.04.01 | TRG3010 | Procure LiAr ATCA Carrier Cards, AMC cards, Powered Crate, Switch Blade, Shelf Manager | 108 | 0% | 2015-01-02 | 2015-02-26 | 2015-09-01 | Procure Comtel 2-slot ATCA crate. John O will ask Sorin about SRC carrier and mezz cards.
1.02.04.01 | TRG3010M | Material cost for Procure LiAr ATCA Carrier Cards, AMC cards, Powered Crate, Switch Blade, Shelf Manager | 108 | 0% | 2015-01-02 | 2015-02-26 |  | John O, Nathan, will get quotes on Comtel crate and SRS cards.
1.02.04.01 | TRG3010MP | Payment for Material cost for Procure LiAr ATCA Carrier Cards, AMC cards, Powered Crate, Switch Blade, Shelf Manager | 1 | 0% | 2015-02-27 | 2015-02-27
1.02.04.01 | TRG3020 | Crate communication with Shelf Manager | 20 | 0% | 2015-03-02 | 2015-03-27 | 2015-08-01 | Communication with shelf manager without SRS cards.
1.02.04.01 | TRG3025 | Integrate real ADDC | 43 | 0% | 2016-04-01 | 2016-06-01
1.02.04.01 | TRG3030 | Procure GBT links and other hardware | 20 | 30% | 2015-03-30 | 2015-04-24 |  | This refers to optical fibers, not GBT transciever chips. Do we buy these or does BNL?
1.02.04.01 | TRG3030M | Material cost for Procure GBT links and other hardware | 20 | 30% | 2015-03-30 | 2015-04-24
1.02.04.01 | TRG3040 | Remote FPGA configuration - Carrier and AMC | 20 | 0% | 2015-04-27 | 2015-05-22 | 2015-11-01 | Several options: Shelf manager or RTM. Hopefully we get software/firmware from Sorin
1.02.04.01 | TRG3050 | Set up ATCA crate hardware (Liquid Argon DPS) | 40 | 0% | 2015-05-26 | 2015-07-21 | 2015-10-01 | I assume this means all communication with Mezz and Carrier has been achieved.
1.02.04.01 | TRG3060 | Incorporate TTC backplane signals | 40 | 0% | 2015-07-22 | 2015-09-16 | 2015-12-01 | Again, this is delayed due to delay in purchasing crate.
1.02.04.01 | TRG3070 | ATCA Hardware setup complete | 0 | 0% |  | 2015-09-16 | 2016-01-01 | This seems to be redundant with line 34 above.
1.02.04.01 | TRG3080 | Port TP Algorithm to LAR system | 60 | 0% | 2015-09-17 | 2015-12-10 |  | Check these dates. May be okay.
1.02.04.01 | TRG3090 | Debug mode - Error monitoring and recovery | 40 | 0% | 2015-12-11 | 2016-02-08 |  | Check these dates. May be okay.
1.02.04.01 | TRG3100 | Trigger data monitor (Raw trigger data) | 40 | 0% | 2016-02-09 | 2016-04-04 |  | Check these dates. May be okay.
1.02.04.01 | TRG3110 | DCS integration | 20 | 0% | 2016-04-05 | 2016-05-02 |  | Check these dates. May be okay.
1.02.04.01 | TRG3120 | MMTP/ATCA system firmware complete | 0 | 0% |  | 2016-05-02 |  | Check these dates. May be okay.
1.02.04.01 | TRG4010 | Backplane (mesh) implementation | 20 | 0% | 2015-09-17 | 2015-10-14 |  | I don't think we use mesh.
1.02.04.01 | TRG4020 | Algrorithm | 30 | 0% | 2015-10-15 | 2015-11-25 |  | What exactly is this?
1.02.04.01 | TRG4030 | Integration with sTGC | 40 | 0% | 2015-11-27 | 2016-01-25 | 2016-04-01 | Seems optimistic.
Module 0 Integration |  |  | 397 |  | 2015-01-02 | 2016-09-20
1.02.04.01 | TRG5010 | Integrate ATCA based Trigger Processor on Module 0 | 60 | 0% | 2016-04-01 | 2016-06-24
1.02.04.01 | TRG5020 | Data collection and analysis | 60 | 0% | 2016-06-27 | 2016-09-20
1.02.04.01 | TRG6010 | Vertical Slice Test Stand | 297 | 0% | 2015-01-02 | 2016-03-01
1.02.04.01 | TRG6010M | Material cost for Vertical Slice Test Stand | 297 | 0% | 2015-01-02 | 2016-03-01
1.02.04.01 | TRG6010T | Travel cost for Vertical Slice Test Stand | 297 | 0% | 2015-01-02 | 2016-03-01
Production |  |  | 418 |  | 2016-07-01 | 2018-02-21
1.02.04.01 | TRG7008 | Wait time to start LiAr ATCA Carrier and AMC cards procurement | 14 | 0% | 2016-07-01 | 2016-07-21
1.02.04.01 | TRG7010M02 | prepare specification - LiAr ATCA Carrier and AMC | 10 | 0% | 2016-07-22 | 2016-08-04
1.02.04.01 | TRG7010M04 | solicitate quote | 15 | 0% | 2016-08-05 | 2016-08-25
1.02.04.01 | TRG7010M06 | select vendor | 5 | 0% | 2016-08-26 | 2016-09-01
1.02.04.01 | TRG7010M08 | procurement paper work and coordination | 20 | 0% | 2016-09-02 | 2016-09-30
1.02.04.01 | TRG7010M10 | LiAr ATCA Carrier and AMC cards procurement oversight | 43 | 0% | 2016-10-03 | 2016-12-01
1.02.04.01 | TRG7010M12 | Inspection | 5 | 0% | 2016-12-02 | 2016-12-08
1.02.04.01 | TRG7010M14 | Material cost for Procure LiAr ATCA Carrier and AMC cards | 3 | 0% | 2016-12-09 | 2016-12-13
1.02.04.01 | TRG7020 | Production test stand hardware | 60 | 0% | 2016-12-14 | 2017-03-09
1.02.04.01 | TRG7020M | Material for Production test stand hardware | 60 | 0% | 2016-12-14 | 2017-03-09
1.02.04.01 | TRG7020MP | Paymet for Material for Production test stand hardware | 1 | 0% | 2017-03-10 | 2017-03-10
1.02.04.01 | TRG7030 | Test stand software | 60 | 0% | 2017-03-13 | 2017-06-05
1.02.04.01 | TRG7035 | Wait for Test Stand | 16 | 0% | 2017-06-06 | 2017-06-27
1.02.04.01 | TRG7040 | Production QA/QC | 60 | 0% | 2017-06-28 | 2017-09-21
1.02.04.01 | TRG7045 | Lag Time Before Shipping | 18 | 0% | 2017-09-22 | 2017-10-17
1.02.04.01 | TRG7050 | Trigger Processor Electronics Shipping | 40 | 0% | 2017-10-18 | 2017-12-13
1.02.04.01 | TRG7055 | Lag Time Before Completion | 17 | 0% | 2017-12-14 | 2018-01-09
1.02.04.01 | TRG7060 | Production complete | 0 | 0% |  | 2018-01-09
1.02.04.01 | TRG7070 | Production Termination Date | 0 | 0% |  | 2018-02-21
NSW FE coordiation |  |  | 383 |  | 2014-10-01 | 2016-03-31
1.02.04.01 | TRG6020 | NSW FE Coordination | 383 | 99% | 2014-10-01 | 2016-03-31